## Projects
|  |  |  | Project Scope Elements |  |  |  |  | Plan |  |  | Project Costs
Building | Problem | Time Critical Need | Building Status | Exterior Wiring | Workstation Wiring | Infrastructure: cabletrays, conduit, raceway | Communication Closets | Networking Equipment | Design done? | Closets identified? | GSF / (# outlets) | Interior Wiring Formula based estimate | Communication Services estimate | Firm Quote
325 Interim Marine Lab II | Cat 3 cabling | No. | Trailer, near MSI trailers | Y | Y | Y | N | Y | N | N | 515 | 1545 | N | N
408 Aquatic Biology Lab | Cat 3 cabling not capable of supporting adequate bandwidth. Relocation of Biology shop will destroy existing communications area and require rewiring. | Possible due to collaborations with PISCO and ICESS | Temporary building. | N | Y | Y | N | Y | Y | N | 7055 | 21165 | N | N
411 Psych Research Facility | Thinnet cabling not capable of supporting adequate bandwidth. | Funding of new NSF grant ($500K 2000/2003) by occupant, locating of post-docs into space. | Removed with construction of parking project. | N | Y | Some raceway required for cosmetic installation. | Y | Y | Prelim | Y | 2520 | 7560 | N | N
429 Psych Grad Facility | Needs wireless networking for intra and exterior wiring | Grad student offices needing laptop access. | Removed with construction of parking project. | Y | Y, or wireless | No, temporary building. | ? | Y | N | Y | 5040 | 15120 | N | N
465 Old Marine Lab (& 508) | Thinnet leg provided via Marine Biotech building. |  | Temporary building. | Y | Y | Y | Y | Y | Y | Y | 5947 | 17841 | N | N
503 Engineering II | Thicknet cable not capable of supporting adequate bandwidth and supporting networking equipment waiting to fail. Redo workstation wiring to provide communication closet structure, rather than ad-hoc cabling and hubs. | Thicknet reliability. |  | N | Y | Y | Y | ? | Prelim | ? | 126247 | 378741 | N | N
504 Bio Instruct Facility | Thinnet cabling not capable of supporting adequate bandwidth and difficulty/coss associated with supporting the technology (availability). | Bandwidth needs due to web based technologies. |  | N | Y | Y | Y | Y | N | Y | 13816 | 41448 | N | N
525 Davidson Library | Workstation wiring and networking hardware to support 84 new public access Infostations. | Public access Infostations would be rolled out over 3 year period. | Renovation planning money begins in 5 years | N | Y | Y | Y | Y | N | Y | -84 | 54600 | N | N
525 Davidson Library | Protect telecommunications hardware in 5 shared Communications/Custodial closets. | Network connectivity as been lost due to accidents in these closets. | Renovation planning money begins in 5 years | N | N | N | Protect what is currently there. | N | N | Y | N/A | N/A | N | N
539 Electron Microscopy Facility | Thinnet through 3 buildings | Supportability of thinnet connection leg spanning 3 buildings. |  | Y | Y | Partial | Y | Y | Y | Y | 2736 | 8208 | N | N
540 Green House | Thinnet through 3 buildings | Supportability of thinnet connection leg spanning 3 buildings. |  | Y | Y | Y | Y | Y | Y | Y | 8209 | 24627 | N | N
544 Noble Hall | Thinnet cabling not capable of supporting adequate bandwidth and difficulty/coss associated with supporting the technology (availability). | Faculty research bandwidth needs increasing dramatically, group projects with PISCO, ICESS & NCEAS. |  | ? | Y | Y | Y | Y | Y | Y | 44310 | 132930 | N | N
551 Psychology | Thinnet cabling not capable of supporting adequate bandwidth and difficulty/coss associated with supporting the technology (availability). | New faculty researcher arriving with post-docs | Renovation in - 7 years | N | Y | Y | Y | Y | Y | Y | 48480 | 145440 | 191293 | N
555 Marine Biotech | IBM Type II cable (Cat 2?), shared with telephone. | Pending Materials, ONR research grants. |  | N | Y | Some | Some raceways already exist in new portion of building, none in labs. | Y | N | Y | 35515 | 106545 | N | N
569 Butler Building | Thinnet | Instructional and research lab development |  | ? | Y | Y | Y | Y | N | Y | 8202 | 24606 | N | N
571 Biology II | Thinnet cabling not capable of supporting adequate bandwidth and difficulty/coss associated with supporting the technology (availability). | Potential new faculty members (Director MSI) arriving January 2001 with high bandwidth needs. |  | N | Y | No, newly installed | Y | Y | Y | Y | 129737 | 389211 | N | N
582 Aviary Trailer | ? | Potential future internet based monitoring. | Temporary building. | N | N | N | N | N | N | N | 520 | 1560 | N | N

## Notes
Notes for ITPG Intrabuilding Wiring Project Analysis
1) | Building - Only departments in Academic Affairs received the call for Intrabuilding Wiring projects.
2) | Project Scope Elements (all page 2) - Y indicates that the project needs this element, N indicates that the element has already been done, or not necessary. This does not mean that all of the scope elements should be covered by Intrabuilding Wiring funds, just that they are required for the project to be complete.
3) | GSF / (# outlets) - Numbers in this column indicate Gross Square Footage for the affected space unless they are in ()'s, in which case they indicate the desired number of communication outlets.
4) | Interior wiring formula based cost estimate as described at http://www.commserv.ucsb.edu/HPAGE/DOCS/comm_plan_guide.htm#budgeting
GSF numbers are multiplied by $3.00 and outlet numbers are multiplied by $650.00.